## RCUcalendar
Team | Project Name | Start Month | End Month | Project Owner | Notes
Communication | CTSO conference materials | January | April | Amanda
Communication | CTE Promotional Toolkit updates | June | September | Amanda | I'm putting future updates on hold until further notice
Communication | Pathways CPMs & FGs | April | August | Amanda
Communication | RCU website | January | December | Amanda | Updated as needed
Communication | RCU desktop calendar | December | December | Amanda
Communication | RCU Promotional Toolkit updates | July | September | Amanda
Communication | Annual Report for ORED | October | December | Amanda
Communication | Connections (Fall) | August | November | Carl
Communication | Connections (Spring) | December | May | Carl
Communication | Connections (Web) | January | December | Carl | Contract specifically calls for posting content every month\, and that requires getting material.
Communication | Curricula Editing | January | December | Carl
Communication | PL/SI Editing | January | December | Carl
Communication | External Comm Editing | January | December | B, H & C | News releases, Annual Report, announcements, etc.
Communication | RCU Quarterly | Quarterly | Quarterly | Carl
Communication | Misc. Curricula Docs Editing | January | December | Carl | Facilities guides, pathways posters, etc.
Communication | School Focus | TBD | TBD | Carl | Usually the same type of schedule as Connections
Communication | Final Review Process | January | December | B, H & C | If we’re going to start a two-editor process of reviewing everything, this needs to be noted.
Communication | Misc. Doc Editing | January | December | B, H & C | There are a lot of things that don’t fit into specific categories/funding streams for which we all act as primary editors. These include: Innovative Institute programs and promotional material, MS ACTE programs, etc.
Communication | Strategic Goals Team Leadership | January | December | A, H & C | We should note this because it’s taking up our T&E.
Communication | Contract Quarterly Updates - Q1 | October | October | Brock
Communication | Contract Quarterly Updates - Q2 | January | January | Brock
Communication | Contract Quarterly Updates - Q3 | April | April | Brock
Communication | Contract Quarterly Updates - Q4 | July | July | Brock
Communication | MDE Annual Report Info Gathering | July | July | Brock
Communication | MDE Annual Report Writing/Editing | August | August | B, H, C
Communication | MDE Annual Report Due | September | September | Brock
Communication | Comm Team Webinars | Oct | Mar | B, H, C, A
PL | Coach U | February | February | Cindy | Spring Meeting
PL | Coach U | April | April | Cindy | School Visits
PL | Coach U | July | July | Cindy | onboarding
PL | Coach U | October | October | Cindy | Fall Training
PL | RCU Professional Development | January | January | Betsey
PL | RCU Professional Development | May | May | Betsey
PL | RCU Professional Development | August | August | Betsey
PL | RCU Professional Development | December | December | Betsey
PL | Innovative Leadership Summit | February | February | Cindy
PL | Innovative Institute | June | June | Cindy
PL | NTI Summer II | June | June | Cindy
PL | Middle School Methods | June | June | Myra
PL | Pathways Methods Courses | July | July | Myra
PL | MSACTE | July | July | Pam/RCU
PL | Professional Development for School Districts | August | August | Myra
PL | New Teacher Induction (NTI) Coaching Visits | January | March
PL | New Teacher Induction (NTI) Coaching Visits | September | November
PL | NTI Late Hire | August | September | Cindy
PL | NTI Regional 1 | October | October | Myra
PL | NTI Regional 2 | January | January | Myra
PL | NTI Regional 3 | March | March | Myra
PL | Early College/Middle College Leadership Assembly | November | November | Myra
PL | Revise SPED Alternate Standards Documents | August | December | Ginny | Fall
PL | Hold writing team meetings to revise the Teacher Resource Guides for SPED | August | December | Ginny | Fall
PL | Revise the IEP Form and the IEP Guidance Document annually to meet any changes in SPED guidelines. | May | August | Ginny | Summer